## Sheet1
BrightTV Growth Roadmap
Workstream | Owner | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Priority | Status
Data model and KPI baseline | BI | 2026-04-21 | 2026-04-27 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | High | Ready
Monday sports campaign design | Programming | 2026-04-28 | 2026-05-11 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | High | Planned
Tuesday music block test | Programming | 2026-04-28 | 2026-05-18 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | High | Planned
25-44 audience paid acquisition | Growth | 2026-05-05 | 2026-06-02 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | High | Planned
Gauteng and Western Cape geo-CRM | CVM | 2026-05-05 | 2026-05-26 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | Medium | Planned
Prime-time reminder journeys | CRM | 2026-05-12 | 2026-06-09 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | Medium | Planned
Measure uplift and optimize | BI + CVM | 2026-05-26 | 2026-06-16 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | High | Planned